Table of Contents

# Lane 1 · Sales · 30-Day Calendar

Goal: 8-15 booked Pre-List Valuation or Buyer Discovery consults in 30 days. Spend assumption: $400-700 in Meta Ads over 30 days (scales by results). Owners: Nikki approves creative; Muhammed builds + monitors.

## Pre-flight blockers (Week 0)

⚠️ Before any ad goes live, confirm: 1. Instagram handle restored or rebranded (currently 404) 2. ManyChat reconfigured against the working IG handle 3. Microsoft Bookings page live with two services: Pre-List Valuation (30m) + Buyer Discovery (30m) 4. BoldTrail webhook tested via Make Scenario 01

If any blocker is unresolved by Wednesday Week 1, ads cannot launch this week.

## Week 1 · Foundation + Creative Build

| Day | What ships | Owner |
| --- | --- | --- |
| Mon | Brief Coffee & Contracts visual templates for the 2 ad creatives | Nikki + Muhammed |
| Tue | Ad copy variants A/B/C drafted using gergacs-post-writer (3 hooks each ad) | Muhammed |
| Wed | Voice Keeper pass on copy; Nikki approves | Nikki |
| Thu | Ad creative built in Canva (IG square 1080×1080 + IG vertical 1080×1920 + FB landscape 1200×628) | Muhammed |
| Fri | Ads loaded in Meta Business Suite, audiences configured | Muhammed |
| Sat | Ads launch (paused) — final review by Nikki | Nikki |
| Sun | Ads go live at 9 AM ET | — |

### Ad #1 · Pre-List Valuation (target: Carolyn persona)

Audience: - Geo: Chatham, Bryan, Effingham counties - Age: 50-72 - Demographics: Homeowners, household income $150k+ - Behaviors: Active on Facebook, engaged with home/lifestyle content

Copy variants:

Hook A: “I’ll show you what the comparables show before I’ll tell you my listing strategy.” Hook B: “After 21 years of appraising Savannah homes, here’s how I think about pricing differently.” Hook C: “What an appraiser-trained perspective sees in your Savannah home that a CMA doesn’t.”

Body (consistent across hooks): “I’m a Realtor and a GA Certified Residential Appraiser — one of the only ones in Savannah with both. When you’re thinking about selling, the right starting point isn’t ‘who will list me at the highest number.’ It’s ‘who will walk me through what the comparables show.’ Let’s have a 30-minute conversation. No pressure, no pitch — a strategic pre-list comparable analysis grounded in 21 years of valuing the Lowcountry.”

Disclaimer (in body or footer): Pre-list comparable analysis is a strategic pricing review — not a USPAP appraisal.

CTA: “Book Your Pre-List Analysis” Destination: ManyChat → keyword SELL → Microsoft Bookings link

Image direction: Savannah homeowner couple (60s, mixed-demographic) on a porch with morning coffee. Live oak with Spanish moss in soft background. Golden hour. Subtle pearl-mark overlay top-right.

### Ad #2 · Relocation Discovery (target: Eleanor persona)

Audience: - Geo: NYC, NJ, CT, DC metro, Northern VA, San Francisco Bay, LA, Boston - Age: 42-65 - Demographics: Homeowners, household income $200k+ - Behaviors: Interest in Georgia + retirement + remote work; recently engaged with travel-to-South content

Copy variants:

Hook A: “Three things California buyers mis-budget their first 90 days in Savannah.” Hook B: “From Brooklyn to Pooler — what surprised her most after the move.” Hook C: “Relocating to Savannah? I’ll walk you through neighborhoods most agents skip.”

Body: “Born and raised in Savannah. 21 years as a Certified Residential Appraiser. I’ve helped relocators from across the country find the part of the Lowcountry that actually fits their life — not just the part on the listing site. 30 minutes, no pressure. Tell me where you’re coming from and what you’re hoping for.”

CTA: “Plan Your Move” Destination: ManyChat → keyword MOVE → Microsoft Bookings link

Image direction: Multi-generational, multi-ethnic family walking Forsyth Park, fountain in soft focus. Warm afternoon light. Subtle “From [origin] to Savannah” overlay if creative supports.

## Week 2 · Live + Iterate

| Day | Action |
| --- | --- |
| Mon | First performance check (gergacs-metrics-reviewer): which hook is winning? |
| Tue | Decision: pause losing hooks, scale winning hooks (10-20% budget bump) |
| Wed | First booked consults appearing — ensure stage triggers fire correctly |
| Thu | Microsoft Bookings page review: any drop-off? Any time-slot gaps? |
| Fri | Mid-week metrics: cost per ManyChat capture, cost per booked |
| Sat-Sun | Ads continue running on autopilot |

Decision thresholds (apply Friday): - If cost per ManyChat capture > $25 after $50 ad spend → kill the worst-performing hook variant - If CTR < 0.8% → kill the worst-performing creative - If ManyChat → BoldTrail conversion < 30% → diagnose: is the keyword reply funnel broken? - If cost per booked < $30 AND consult-to-engagement > 35% → scale spend 25%

## Week 3 · Add Retargeting + Variant 2

| Day | Action |
| --- | --- |
| Mon | Build retargeting audience: anyone who interacted with Lane 2 content past 30 days |
| Tue | Build variant 2 of Ad #1 (Pre-List Valuation): more direct “what your home is worth” angle |
| Wed | Launch retargeting ad set with mid-funnel CTA (FAQ + Microsoft Bookings) |
| Thu | First mid-month deep dive (Day 14): performance by ad creative + persona × hook |
| Fri | Decisions briefed for week 4 |
| Sat-Sun | Continue runs |

### Retargeting ad creative

Audience: People who engaged with any Lane 2 content (Reels watched 50%+, blog page views, IG profile clicks) past 30 days Hook: “Saw you stopped by — here’s the question I get most often.” Body: “Whether you’re 30 days or 30 months from your next move, the right time for the conversation is whenever it’s useful to you. No pressure. No pitch. Just answers.” CTA: “Pick a 30-minute slot” Destination: Microsoft Bookings (skip ManyChat — they’re warm)

## Week 4 · Convert + Reflect

| Day | Action |
| --- | --- |
| Mon | Final mid-month metrics; build a list of bookings for the week |
| Tue-Thu | Nikki conducts consults. Each booked consult is a campaign success. |
| Fri | Final Day 28 metrics review; cost-per-booked, cost-per-engagement-stage |
| Sat | Weekend Reels recap: tease 1-2 of week’s highlights as marketing-lane content (closes Lane 1 → Lane 2 loop) |
| Sun | Day 30 report briefed (gergacs-metrics-reviewer with full month data) |

## Lane 1 KPIs (track weekly)

| Metric | Week 1 target | Week 4 target | Source |
| --- | --- | --- | --- |
| Ad spend | $0-150 | $400-700 cumulative | Meta Ads |
| ManyChat captures | 3-8 | 30-50 cumulative | ManyChat |
| BoldTrail contacts created | 3-8 | 30-50 cumulative | BoldTrail |
| Microsoft Bookings booked | 1-3 | 8-15 cumulative | MS Bookings |
| Consult → engagement rate | (n/a yet) | 25%+ | BoldTrail stage |
| Cost per booked consult | (n/a yet) | ≤ $40 | Calculated |
| Closed deals attributable | 0 | 1+ | SkySlope |

## Lane 1 follow-up sequence (BoldTrail flows)

After every booked consult, Outlook sends via Make Scenario 02:

| Stage | Email | Timing |
| --- | --- | --- |
| Booked | “Looking forward to our conversation” + prep checklist | Immediate (on Bookings creation) |
| Day-of | Reminder + map / Zoom link | 1 hour before |
| Post-call | Recap + decision next step + Microsoft Bookings link for next call | Same day |
| +3 days (if no decision) | “Just checking in — here’s what we discussed” | +3 days |
| +7 days (if no decision) | One specific market data point relevant to their case | +7 days |
| +30 days (if still warm) | Re-engage: “Curious whether the timing has shifted for you” | +30 days |

This sequence is in make_scenarios/02_pearl_stage_triggers.json from the ops package — Lane 1 just lights it up.

## What kills Lane 1 (escalation triggers)

- Meta ad account flagged or restricted → escalate immediately to Meta Business Support

- Microsoft Bookings page unavailable for 24+ hours → emergency fix

- BoldTrail webhook silent for 24+ hours → emergency Make scenario investigation

- Single booked consult complaining about pre-call mismatch → review the ManyChat reply, the welcome email, and the prep email; one of them is creating a wrong expectation