Table of Contents

# Lane 2 · Marketing · 30-Day Calendar

Goal: Build the audience that compounds for the next 12 months. Lane 2 doesn’t optimize for next-week consults; it builds the inventory of warm prospects Lane 1 can later retarget.

Targets: - IG followers +25-40% (~40-65 new followers on a 159-follower base — actual realtor handle once restored) - Newsletter subscribers +100 - 3+ blog posts published, 1-2 ranking by day 90 - YouTube subs +50-150 - 1 Reel hits 10k+ reach

Owners: Nikki briefs / approves; Muhammed builds + schedules.

## Pre-flight blocker

⚠️ Instagram handle must be restored before Week 1 of Lane 2. Without IG, this lane runs at 60% capacity (FB + YouTube + blog only).

## Weekly cadence (template — repeats Weeks 1-4)

| Day | What ships | Channel |
| --- | --- | --- |
| Mon | Monday Brief from gergacs-metrics-reviewer | Internal |
| Mon-Tue | Brief next week’s content in Notion Lighthouse · 5-7 pieces | Notion |
| Tue | Hero asset shoot / record (1 YT long-form + 3-5 source clips for Reels) | YouTube |
| Wed | Edit hero asset · pull Reel clips · build carousel via Coffee & Contracts | Canva + C&C |
| Thu | Schedule the week’s posts in Metricool | Metricool |
| Fri | YouTube long-form drops 6 AM ET · IG Reel #1 (Tue 11a–1p planned) · FB native upload Friday 4p | YT, IG, FB |
| Sat | IG Story summary of the week’s hero · TikTok cross-post via Repurpose.io | IG, TikTok |
| Sun | Long-form blog post publishes from the week’s hero asset | WordPress |

## Week 1 — Hero topic: “What an appraiser sees that an agent misses”

Why this hero: Highest-leverage credential play. Differentiator-led. Sets the tone for the campaign.

### YouTube long-form (Thursday drop)

Title: “What I See in 60 Seconds Walking a Savannah Home — From a Realtor + Appraiser” Length: 8-10 min Outline: 1. Quick intro — Nikki, dual credential 2. Walkthrough of one Savannah listing (recent, with permission), narrating in real-time 3. Three things she’d flag for a buyer (foundation, water, finish quality) 4. Three things she’d flag for a seller (condition vs price) 5. Why this matters in Savannah specifically — historic, coastal, weather considerations 6. CTA: book a Pre-List Valuation OR Buyer Discovery on Microsoft Bookings

### Reel clips from the long-form (3 Reels)

- “POV: I’m an appraiser walking the home you’re about to bid on”

- “The 3 things sellers swear add value that I, as an appraiser, will not give you a dime for”

- “What 21 years of appraising taught me about Savannah waterfront pricing”

### Carousel (IG + FB)

“Five questions every Savannah seller asks me — answered” — 7 slides, lead-magnet PDF link in bio

### Blog post (Sunday publish)

Title: “Pre-Listing Appraisal in Savannah: Why I Recommend One Before You Price” Target: Carolyn persona. SEO target: “pre-listing appraisal Savannah” Length: 800-1100 words Outline: (per gergacs-seo-briefer brief) - What is a pre-listing appraisal - Why it’s different from a CMA - The four scenarios where it matters most (estate, divorce, downsizing, luxury) - One real Savannah case study (anonymized) - What an appraisal looks like, step by step - Booking CTA

### TikTok (3 posts via Repurpose.io)

- Cross-posts of Reels 1, 2, 3 (with platform-native edit pass)

### LinkedIn (2 posts)

- Long-form: “21 years appraising the Lowcountry — what every relocation HR manager should ask before placing an exec in Savannah”

- Carousel PDF: “The estate-and-divorce appraisal checklist most Georgia attorneys don’t request”

## Week 2 — Hero topic: “Neighborhood honesty”

Why this hero: Place-based identity is unclaimed by competitors. Pure greenfield.

### YouTube long-form

Title: “Ardsley Park vs Habersham vs Skidaway: An Honest Walkthrough” Length: 10-12 min · drone + walking + neighborhood interview

### Reel clips (3 Reels)

- “Three Ardsley Park porches I’d buy just for the morning light”

- “Why I tell relocators to spend a weekend in [neighborhood] before they buy there”

- Skidaway-specific: “What it’s actually like to live behind the gate”

### Carousel

“How to choose a Savannah neighborhood without seeing them all yourself” — 8 slides covering 4 trade-offs

### Blog post

Title: “Ardsley Park Historic Homes: What Buyers Should Know About Valuation” Target: Marcus persona · SEO target: “Ardsley Park homes for sale + valuation”

### TikTok

- 3 cross-posts via Repurpose.io

- 1 native-recorded “Tell me you’re moving to Savannah without telling me” trend post

### Facebook

- 3 native posts (1 Reel native upload, 1 community-warm photo post, 1 market-update bullet)

- Activate “What I’m seeing this week” Tuesday market series

## Week 3 — Hero topic: “Relocator’s truth”

Why this hero: Relocator persona (Eleanor) is the highest-LTV target. Lane 2 builds the audience Lane 1 retargets.

### YouTube long-form

Title: “Hurricane, Flood, Insurance: The Relocation Truth Talk Zillow Won’t Show You” Length: 12-15 min · sit-down with a local Savannah insurance broker

### Reel clips (3)

- “Three things California buyers mis-budget the first 90 days in Savannah”

- “From Brooklyn to Pooler — what surprised her most after the move” (client interview clip if available)

- “The four costs no one warns you about when moving south”

### Carousel

“Relocator’s checklist: 12 things to verify before you sign anything in Savannah”

### Blog post

Title: “Hunter Army Airfield PCS Guide: Best Neighborhoods for Military Families” Target: Eleanor (military subset) · SEO target: “Hunter AAF housing relocation”

### Facebook + LinkedIn

- LinkedIn long-form: “After 21 years appraising the Lowcountry, here’s what I tell every relocation HR contact”

- FB Live (15 min): “Ask a Savannah Appraiser” Tuesday lunchtime — Q&A from comments + DMs

## Week 4 — Hero topic: “Pearl found” (listing-led)

Why this hero: Listings are the most direct revenue. By Week 4, the lane has built enough audience to justify weight here.

### YouTube long-form

Title: “Pearl Found: Inside [neighborhood] [listing address]” — full home tour with appraiser commentary Length: 6-8 min · driven by the listing’s actual photo shoot

### Reel clips

- Listing walkthrough Reel (3 clips, week-long campaign)

- 1 “what an appraiser values about this home” Reel

### Carousel + FB

- Standard listing distribution package (per gergacs-listing-describer)

### Blog post

Title: “Tybee Island Beachfront: Flood Zones, Insurance, and What Affects Resale” Target: Eleanor / Marcus · SEO target: “Tybee Island beachfront homes”

## Lane 2 content production budget

Time per week (consistent across 4 weeks): - Nikki: 2 hours (Tue shoot/record + Mon brief approval + occasional voiceover) - Muhammed: 8-10 hours (build, schedule, monitor, repurpose) - Total: ~12 hours/week of human time

Outputs per week: - 1 YouTube long-form (8-15 min) - 3-4 Instagram Reels (45-60s) - 1 Instagram carousel - 5+ Instagram Stories - 3 Facebook posts - 3-5 TikTok posts (mostly via Repurpose.io) - 2 LinkedIn posts - 1 blog post (Sunday publish) - 1 newsletter sub-piece (BoldTrail)

## Lane 2 KPIs (track weekly)

| Metric | Week 1 target | Week 4 target | Source |
| --- | --- | --- | --- |
| YouTube subs | +5-15 | +50-150 cumulative | YT Studio |
| YT watch hours | +5-15 | +30-60 cumulative | YT Studio |
| IG followers | +5-15 | +40-65 cumulative | Metricool |
| Top Reel reach | 2-5k | At least 1 ≥ 10k | Metricool |
| Newsletter subs | +10-30 | +100 cumulative | BoldTrail |
| Blog sessions | (no data yet) | up vs prior 30 days | GA |
| TikTok views | track | track | Native |
| LinkedIn impressions | 500-1500 | 4-6k cumulative | Native |

## Anti-pattern flags for Lane 2

- ❌ Posting just to post (no clear persona, hook, or CTA stage)

- ❌ Re-using competitor imagery or generic stock real-estate photography (use 01_strategy/savannah_image_library.md)

- ❌ Letting blog posts go up untagged for taxonomy and meta description

- ❌ Pearl metaphor in 80%+ of content — saturation kills the metaphor

- ❌ Multi-CTA confusion (“buy or sell or get an appraisal!”)

## Lane 2 → Lane 1 handoff

Every Lane 2 piece that performs above 2x average reach gets: 1. A retargeting audience created (people who engaged) → fed into Lane 1 ad sets 2. A “second wind” promotion — boost spend $50-100 on the post itself 3. Surfaced in next week’s Monday Brief as “do more of this”

The interlock is what makes the system compound.