Table of Contents

# Skills Needed for the 30-Day Campaign

What human skills, software access, and credential states are required to execute this campaign cleanly.

## Per-person breakdown

### Nikki (the principal)

Time commitment: ~ 6-8 hours per week during the campaign - 2 hrs · Monday Brief review + decisions - 2 hrs · Lane 2 content shoot or record (Tue or Wed) - 1 hr · Lane 3 personal touches (Wed) - 30 min · Lane 3 review sweep / referral activation (Fri) - 1-2 hrs · Microsoft Bookings consults (varies) - 30 min · Friday week-recap

Skills: - ✅ On-camera presence (already has from existing YT channel) - ✅ Brand voice articulation - ✅ Appraiser-credential storytelling - ⚠️ USPAP-disciplined marketing language (this campaign trains it explicitly)

Software access required: - BoldTrail (CRM access + admin for drip campaign edits) - Notion (workspace + databases imported) - Microsoft Bookings (admin) - Outlook (campaign account) - Gmail (gergacsrealty@gmail.com) - Meta Business Suite (admin) - Instagram Business Profile (admin — once handle restored) - Facebook Page (admin) - YouTube channel (creator dashboard) - Coffee & Contracts (subscription active) - Canva (active account) - LinkedIn Premium (recommended for outreach features)

### Muhammed (the VA)

Time commitment: ~ 8-12 hours per week - 4 hrs · Lane 2 content build (Coffee & Contracts + Canva + Metricool scheduling) - 2 hrs · Make scenario maintenance + monitoring - 1-2 hrs · Trello task execution (Lane 3 logistics, listing prep) - 1 hr · Weekly metrics pull for Monday Brief - 1-2 hrs · Coordination + documentation

Skills: - ✅ Make.com scenario building (importing JSON, connecting credentials, debugging webhooks) - ✅ Notion database administration - ✅ Canva intermediate (he likely already has this) - ✅ Coffee & Contracts template customization - ✅ Metricool scheduling - ⚠️ Repurpose.io workflow setup (training: ~ 30 minutes; cross-posts auto-fire after that) - ⚠️ Light HTML/CSS for the gergacsappraisals.com MVP rebuild (or hand off to a third party) - ✅ Light copywriting (using the agents in 04_agents/)

Software access required: - Make.com (admin) - Notion (editor on the workspace) - Canva - Coffee & Contracts (login) - Metricool (login) - Trello (admin on the relevant boards) - WordPress (editor on the lifestyle site + appraisal site once built) - Repurpose.io (admin)

### Shawn (Value to Victory · designer / strategist)

Time commitment: ~ 4-6 hours total over the campaign - Initial: package handoff (this delivery) - Day 14 mid-month: deep dive review - Day 30: full month report + month 2 planning - Ad-hoc: emergency support when something breaks

## Software access checklist

| Tool | Who needs it | Access level | Notes |
| --- | --- | --- | --- |
| BoldTrail (KVCore) | Nikki, Muhammed | Admin / Editor | API key needed for Make scenarios |
| ManyChat | Muhammed (build), Nikki (oversight) | Admin | Webhook access for Make integration |
| Make.com | Muhammed | Admin | Free tier likely sufficient for first 3 scenarios |
| Notion | Both | Workspace owner / editor | Import the 4 CSVs from the ops package |
| Microsoft Bookings | Nikki (owner), Muhammed (read) | Admin | Two services live: Pre-List Comparable Analysis + Buyer Discovery |
| Outlook | Nikki | Account holder | Used for personal touches, lead welcomes, drip emails |
| Gmail (gergacsrealty@gmail.com) | Nikki | Account holder | Marketing-facing inbox |
| Meta Business Suite | Both | Admin | Includes Facebook Page + Instagram Business Profile |
| Instagram | Nikki | Business Profile owner (once handle restored) | Critical pre-flight blocker |
| YouTube Studio | Nikki, Muhammed | Owner / Manager |  |
| TikTok | Nikki | Pro account |  |
| LinkedIn | Nikki | Premium recommended |  |
| Coffee & Contracts | Nikki + Muhammed | Subscription |  |
| Canva | Nikki + Muhammed | Pro recommended |  |
| Metricool | Muhammed (build), Nikki (review) | Premium recommended | UTM auto-append feature is a Premium feature |
| Repurpose.io | Muhammed | Subscription |  |
| PropStream | Nikki | Subscription | Used for investor list-building (Lane 3 supplement) |
| WordPress (lifestyle site) | Both | Editor |  |
| WordPress (appraisal site, NEW) | Both | Admin (once built) | Pre-flight blocker |
| Matrix MLS | Nikki | Member |  |
| iHomefinder | Nikki | Subscription |  |
| SkySlope | Nikki | Member |  |
| ZipForms | Nikki | Member |  |
| Trello | Muhammed (admin), Nikki (member) |  |  |
| Google Search Console | Both | Property owner / contributor | For SEO tracking on the lifestyle + new appraisal site |
| Google Business Profile (Realty) | Nikki | Owner | Pre-flight blocker — claim/optimize |
| Google Business Profile (Appraisal) | Nikki | Owner | Pre-flight blocker — claim/optimize |
| Google Analytics | Both | Admin / View | Site Kit on WordPress connects this |

## Credentials / legal pre-flight

| Item | Status | Action |
| --- | --- | --- |
| Nikki’s Realtor license (GA) | Active | — |
| Nikki’s Certified Residential Appraiser license (GACR287636) | Active | — |
| Brokerage affiliation (Next Move Real Estate) | Active | — |
| Errors & Omissions insurance | Carried by Next Move | Confirm coverage covers marketing activity |
| USPAP CE current | Confirm with Nikki | Required to maintain Appraiser license |
| Marketing review by brokerage | Required for compliance | Brief Next Move on the 30-day campaign + ad creative |

## Skills the campaign trains

By day 30, both Nikki and Muhammed will have built durable capacity in:

### Nikki

- USPAP-compliant marketing language (this is non-trivial — most agents never learn it)

- Voice-keeper discipline (using the agent skill before posts ship)

- Microsoft Bookings as the close mechanism

- Lane 3 ritual (Wednesday + Friday) as a permanent practice

- Agent prompt usage (Claude / ChatGPT for drafting and refinement)

### Muhammed

- Make scenario design (3 importable + can build new ones from the patterns)

- Notion database administration

- Coffee & Contracts → Canva → Metricool full content production workflow

- Repurpose.io configuration

- Monday Brief generation from raw metrics

- Trello as the tactical task layer

## What this campaign does NOT require

- A new website build (the brand site at gergacs-site branch is delivered with this engagement)

- Hiring additional staff

- Switching CRMs (BoldTrail stays — this campaign is built around it)

- Changing brokerages

- Net-new tool subscriptions beyond what she already has, EXCEPT possibly Repurpose.io if not already active

## Skill gaps to flag

If any of these are weak, address before launch:

- Microsoft Bookings setup — if not yet configured with two services (Pre-List Comparable Analysis + Buyer Discovery), set up week 0

- ManyChat keyword sequences — confirm all 8 are live and tested with the new IG handle

- BoldTrail API access — Muhammed needs this for the Make scenarios; if API is not enabled on her plan, escalate to BoldTrail support

- Brokerage marketing review process — clarify with Next Move whether ad creative needs review before launch

- GBP claim status — verify before Lane 3 review collection sweep starts firing reviews into a non-existent profile